## PUR-F212
PURCHASING DEPARTMENT REQUEST FOR PROPOSAL (RFP) PROCESS TIMELINE ESTIMATOR | [5 empty] | Expected BOT Schedule
Complete the highlighted boxes to calculate the estimated time necessary to complete a formal Request for Proposal (RFP) solicitation. The Purchsaing Department needs a minimum of 2 weeks to develop an RFP, the larger the project, the longer the lead time. | [7 empty] | When January 1, July 4, November 11, or December 25 falls on a Saturday, the preceding Friday is the observed legal holiday. If these days fall on Sunday, the following Monday is the observed holiday.
DISCLAIMER: This RFP Timeline Process Estimator is a tool to aid in the planning process for a formal RFP. This tool is only meant to provide an estimate of the timeline and not meant to be a guarantee of when the process will be complete. There are many factors that could cause the timeline to be extended.
Process Activity | Time to Complete |  | Est. Date | Date | Staff Reports Due to Andrea | Board Services Deadline | Meeting Date | Date | Holiday | NAC 284.255
Today (Auto-Populates) |  |  |  | 2024-10-09 | 2024-07-05 | 2024-07-10 | 2024-07-23 | 2024-12-30 | New Year's Day | January 1st
RFP Release | 3 | Weeks from Today | 2024-10-30 | 2024-10-30 | 2024-07-26 | 2024-07-31 | 2024-08-13 | 2024-01-15 | Martin Luther King Day | Third Monday in January
Deadline for Questions | 2 | Weeks from Release | 2024-11-13 | 2024-11-13 | 2024-08-09 | 2024-08-14 | 2024-08-27 | 2024-02-19 | President's Day | Third Monday in February
Addendum Q&A Posted | 1 | Weeks from Questions Deadline | 2024-11-20 | 2024-11-20 | 2024-08-23 | 2024-08-28 | 2024-09-10 | 2024-05-27 | Memorial Day | Last Monday in May
Proposal Opening/Due | 2 | Weeks from Addendum QA Posted | 2024-12-04 | 2024-12-04 | 2024-09-06 | 2024-09-11 | 2024-09-24 | 2024-07-04 | Independence Day | July 4th
Proposal Review Meeting | 2 | Weeks from Proposal Opening/Due | 2024-12-18 | 2024-12-18 | 2024-10-04 | 2024-10-09 | 2024-10-22 | 2024-09-02 | Labor Day | First Monday in September
Issue Notice of Finalists | 1 | Day from Proposal Review Meeting | 2024-12-19 | 2024-12-19 | 2024-10-24 | 2024-10-30 | 2024-11-12 | 2024-10-25 | Nevada Day | Last Friday in October
Deadline for References | 1 | Weeks from Proposal Review Meeting | 2024-12-29 | 2024-12-31 | 2024-11-08 | 2024-11-13 | 2024-11-26 | 2024-11-11 | Veterans Day | November 11th
Vendor Interviews & Presentations | 2 | Weeks from Proposal Review Meeting | 2025-01-01 | 2025-01-02 | 2024-11-22 | 2024-11-26 | 2024-12-10 | 2024-11-28 | Thanksgiving Day | Fourth Thursday in November
Letter of Intent sent for Review | 1 | Weeks from Vendor Interviews & Presentations | 2025-01-08 | 2025-01-08 | 2024-12-27 | 2025-01-02 | 2025-01-14 | 2024-11-29 | Family Day | Friday following the Fourth Thursday in November
Letter of Intent | 1 | Weeks from Letter of Intent sent for Review | 2025-01-17 | 2025-01-17 | 2025-01-10 | 2025-01-15 | 2025-01-28 | 2024-12-25 | Christmas Day | December 25th
Appeal Window Closes | 5 | Days from Letter of Intent | 2025-01-24 | 2025-01-24 | 2025-01-24 | 2025-01-29 | 2025-02-11 | 2025-01-01 | New Year's Day | January 1st
Contract Negotiations *Contract negotiations can take 1-4 weeks or longer depending on may factors including number of items that need to be negotiated, responsiveness of the vendor to requested changes, and complexity of the project* | 2 | Weeks from Letter of Intent | 2025-01-31 | 2025-01-31 | 2025-02-07 | 2025-02-12 | 2025-02-25 | 2025-02-17 | President's Day | Third Monday in February
Est. BOT Staff Report Submission Due |  |  | 2025-02-12 | 2025-02-12 | 2025-02-21 | 2025-02-26 | 2025-03-11 | 2025-05-26 | Memorial Day | Last Monday in May
Est. BOT Approval |  |  | 2025-02-25 | 2025-02-25
Issue Notice of Award | 1 | Days from Approval | 2025-02-26 | 2025-02-26 | 2025-03-21 | 2025-03-26 | 2025-04-08 | 2025-07-04 | Independence Day | July 4th
[5 empty] | 2025-04-04 | 2025-04-09 | 2025-04-22 | 2025-09-01 | Labor Day | First Monday in September
[5 empty] | 2025-04-25 | 2025-04-30 | 2025-05-13 | 2025-10-31 | Nevada Day | Last Friday in October
[5 empty] | 2025-05-09 | 2025-05-14 | 2025-05-27 | 2025-11-11 | Veterans Day | November 11th
[5 empty] | 2025-05-23 | 2025-05-28 | 2025-06-10 | 2025-11-27 | Thanksgiving Day | Fourth Thursday in November
[5 empty] | 2025-06-06 | 2025-06-11 | 2025-06-24 | 2025-11-28 | Family Day | Friday following the Fourth Thursday in November
[8 empty] | 2025-12-25 | Christmas Day | December 25th
[8 empty] | 2026-01-01 | New Year's Day | January 1st
[8 empty] | 2026-01-19 | Martin Luther King Day | Third Monday in January
[8 empty] | 2026-02-16 | President's Day | Third Monday in February
[8 empty] | 2026-05-25 | Memorial Day | Last Monday in May
[8 empty] | 2026-07-04 | Independence Day | July 4th
[8 empty] | 2026-09-07 | Labor Day | First Monday in September
[8 empty] | 2026-10-27 | Nevada Day | Last Friday in October
[8 empty] | 2026-11-11 | Veterans Day | November 11th
[8 empty] | 2026-11-26 | Thanksgiving Day | Fourth Thursday in November
[8 empty] | 2026-11-27 | Family Day | Friday following the Fourth Thursday in November
[8 empty] | 2026-12-25 | Christmas Day | December 25th
Formulas:
Date = WORKDAY(([Est. Date]-1),1,Holidays)
Staff Reports Due to Andrea = [Board Services Deadline]-5
Board Services Deadline = [Meeting Date]-13
Est. Date = [Date, row above]+([Time to Complete]*7)
Est. Date = [Est. Date, row above]+([Time to Complete]*7)