## Slide 1: Vaughn MS & IB MYP
October 27, 2020
SPP Update #2

## Slide 2: Professional Development
PROGRESS *Language Objectives 11/3/2020 *IB Global Contexts 9/30/2020 *IB Approaches to Learning 9/16/2020 *PLC creating norms 10/28/2020 | BARRIERS *20 new teachers *COVID social distancing & absences | NEXT STEPS *PLC re-norming....new team...new norms *14 teachers to attend IB subject specific workshops in 20-21 school year *Co-teacher training for special and general ed teachers

## Slide 3: COVID updates
PROGRESS *automated attendance procedure for distance learners *teachers are starting to "stream" live instruction from their in-person classes to their distance learners | BARRIERS *problematic attendance among distance, in-person and hybrid learners *some teachers not yet "streaming" instruction causing a heavy workload/burnout *reduced instructional time due to COVID, technical difficulties, and smoke days | NEXT STEPS *PD for teachers to support transition to tech-distance and "streaming" instruction *maintain social distancing to allow for maximized in-person instruction

## Slide 4: Staffing
PROGRESS *15 teachers hired between late July and August following a COVID related hiring freeze *only 1 vacant licensed teaching position remains | BARRIERS *20 teachers new to the building (15 new to WCSD) ...no qualified applicants for last math vacancy as of 10/29/2020 **Professional development ...starts over....can't progress to more advanced levels **Must start at Category 1 IB trainings rather than have some teachers progress to Category 2 trainings | NEXT STEPS *hire a HQ teacher for the last remaining licensed position - math *reduce teacher turnover rate *support teachers and provide high quality professional development

## Slide 5: Family Engagement
PROGRESS *SPP meeting via Zoom with parents attending *Facebook and Twitter sites *ongoing tech support for families | BARRIERS * COVID *Attendance low due to ZOOM and distance engagement | NEXT STEPS *5 parent engagement activities planned for November thru May

## Slide 6: Curriculum, Instruction & Assessment
PROGRESS *Teachers are starting to "stream" live instruction during class time to distance learners *change to 7 period day rather than block while on hybrid schedule to ensure students have Math, ELA every day they are in building | BARRIERS *high Chronic Absenteeism *high failure rate due to absenteeism and distance learning difficulties *long term substitute in Math 8 due to a lack of qualified candidates | NEXT STEPS *14 staff members to IB professional development workshops *2-hour PD session on Language Objectives *2-hour PD session on ELLevation data/strategies software *focus on rigor, IB, SWRL

## Slide 7: Curriculum, Instruction & Assessment #2
PROGRESS *teachers starting to live stream instruction which benefits distance learners * | BARRIERS **COVID and related chronic attendance problems *Co-teaching strategies training is needed *Language Objective training is needed *Staffing *Smoke days, COVID, distance learning | NEXT STEPS *Training needed on co-teaching strategies *Training for all teachers needed using language objectives *Focus on improving opportunities for multiple students to SWRL Speak, Write, Read & Listen

## Slide 8: Curriculum, Instruction, Assessment #3
PROGRESS *5 Shadowing events planned to shadow EL students to monitor opportunities for participation in SWRL *6 planned Instructional Rounds to include teachers, administration, and EL district staff | BARRIERS *lack of subs although funding is available | NEXT STEPS *Conduct planned Shadowing events *Conduct planned Snapshot/Walkthrough classroom visits *Conduct PD/reflection/PLC to analyze Shadowing & Walkthrough data